## Sheet1
| Initiating |  |  | Planning |  |  | Executing |  |  | Monitoring and Controlling |  |  | Closing
Integration Management | Develop Project Charter |  |  | Develop Project Management Plan |  |  | Direct and Manage Project Work |  |  | Monitor and Control Project Work |  |  | Close Project or Phase
| Business Documents | Expert Judgement | Project Charter | Project Charter | Expert Judgment | Project Management Plan | Project Management Plan | Expert Judgement | Deliverables | Project Management Plan | Expert Judgement | Work Performance Reports | Project Charter | Expert Judgement | Project Documents Updates
| Agreements | Data Gathering | Assumption Log | Outputs from Other Processes | Data Gathering |  | Project Documents | Project Management Information System | Work Performance Data | Project Documents | Data Analysis | Change Requests | Project Management Plan | Data Analysis | Final Product, Service, or Result Transition
| Enterprise Environmental Factors | Interpersonal and Team Skills |  | EEFs & OPAs | Interpersonal and Team Skills |  | Approved Change Requests | Meetings | Issue Log | Work Performance Information | Decision Making | PM Plan Updates | Project Documents | Meetings | Final Report |  | I | P | E | M&C | C
| Organizational Process Assets | Meetings |  |  | Meetings |  | EEFs & OPAs |  | Change Requests | Agreements | Meetings | Project Documents Updates | Accepted Deliverables |  | OPAs Updates | Int | x | x | x | x | x
[9 empty] | PM Plan Updates | EEFs & OPAs |  |  | Business Documents |  |  | Scope |  | x |  | x
[9 empty] | Project Documents Updates |  |  |  | Agreements |  |  | Sched |  | x |  | x
[9 empty] | OPAs Updates |  |  |  | Procurement Documentation |  |  | Cost |  | x |  | x
[13 empty] | Organizational Process Assets |  |  | Qual |  | x | x | x
[7 empty] | Manage Project Knowledge |  |  | Perform Integrated Change Control | [5 empty] | Res |  | x | x | x
[7 empty] | Project Management Plan | Expert Judgment | Lessons Learned Register | Project Management Plan | Expert Judgement | Approved Change Requests |  |  |  | Comm |  | x | x | x
[7 empty] | Project Documents | Knowledge Management | PM Plan Updates | Project Documents | Change Control Tools | PM Plan Updates |  |  |  | Risk |  | x | x | x
[7 empty] | Deliverables | Information Management | OPAs Updates | Work Performance Reports | Data Analysis | Project Documents Updates |  |  |  | Proc |  | x | x | x
[7 empty] | EEFs & OPAs | Interpersonal and Team Skills |  | Change Requests | Decision Making |  |  |  |  | Stake | x | x | x | x
[10 empty] | EEFs & OPAs | Meetings
Scope Management |  |  |  | Plan Scope Management | [5 empty] | Validate Scope
|  |  |  | Project Charter | Expert Judgment | Scope Management Plan |  |  |  | Project Management Plan | Inspection | Accepted Deliverables
|  |  |  | Project Management Plan | Data Analysis | Requirements Management Plan |  |  |  | Project Documents | Decision Making | Work Performance Information
|  |  |  | EEFs & OPAs | Meetings |  |  |  |  | Verified Deliverables |  | Change Requests
[10 empty] | Work Performance Data |  | Project Documents Updates
|  |  |  | Collect Requirements | [5 empty] | Control Scope
|  |  |  | Project Charter | Expert Judgment | Requirements Documentation |  |  |  | Project Management Plan | Data Analysis | Work Performance Information
|  |  |  | Project Management Plan | Data Gathhering | Requirements Traceability Matrix |  |  |  | Project Documents |  | Change Requests
|  |  |  | Project Documments | Data Analysis |  |  |  |  | Work Performance Data |  | PM Plan Updates
|  |  |  | Business Documents | Decision Making |  |  |  |  | OPAs |  | Project Documents Updates
|  |  |  | Agreements | Data Representation
|  |  |  | EEFs & OPAs | Interpersonal and Team Skills
Context Diagram
Prototypes
Define Scope
|  |  |  | Project Charter | Expert Judgement | Project Scope Statement
|  |  |  | Project Management Plan | Data Analysis | Project Documents Updates
|  |  |  | Project Documents | Decision Making
|  |  |  | EEFs & OPAs | Interpersonal and Team Skills
Product Analysis
Create WBS
|  |  |  | Project Management Plan | Expert Judgment | Scope Baseline
|  |  |  | Project Documents | Decomposition | Project Documents Updates
EEFs & OPAs
Schedule Management |  |  |  | Plan Schedule Management | [5 empty] | Control Schedule
|  |  |  | Project Charter | Expert Judgement | Schedule Management Plan |  |  |  | Project Management Plan | Data Analysis | Work Performance Information
|  |  |  | Project Management Plan | Data Analysis |  |  |  |  | Project Documents | Critical Path Method | Schedule Forecasts
|  |  |  | EEFs & OPAs | Meetings |  |  |  |  | Work Performance Data | Project Management Information System | Change Requests
[10 empty] | OPAs | Resource Optimization | PM Plan Updates
|  |  |  | Define Activities | [6 empty] | Leads and Lags | Project Documents Updates
|  |  |  | Project Management Plan | Expert Judgement | Acvity List |  |  |  |  | Schedule Compression
|  |  |  | EEFs & OPAs | Decomposition | Activity Attributes
[5 empty] | Rolling Wave Planning | Milestone List
[5 empty] | Meetings | Change Requests
PM Plan Updates
Sequence Activities
|  |  |  | Project Management Plan | Precendence Diagram. Method (et. al.) | Project Schedule Network Diagrams
|  |  |  | Project Documents | Dependency Determination and Integration | Project Documents Updates
|  |  |  | EEFs & OPAs | Leads and Lags
Project Management Information System
Estimate Activity Durations
|  |  |  | Project Management Plan | Expert Judgment | Duration Estimates
|  |  |  | Project Documents | Analogous Estimating | Basis of Estimates
|  |  |  | EEFs & OPAs | Parametric Estimating | Project Documents Updates
Three-Point Estimating
Bottom-Up Estimating
Data Analysis
Decision Making
Meetings
Develop Schedule
|  |  |  | Project Management Plan | Schedule Network Analysis | Schedule Baseline
|  |  |  | Project Documents | Critical Path Method | Project Schedule
|  |  |  | Agreements | Resource Optimization | Schedule Data
|  |  |  | EEFs & OPAs | Data Analysis | Project Calendars
[5 empty] | Leads and Lags | Change Requests
[5 empty] | Schedule Compression | PM Plan Updates
[5 empty] | Project Management Information System | Project Documents Updates
Agile Release Planning
Project Cost Management |  |  |  | Plan Cost Management | [5 empty] | Control Costs
|  |  |  | Project Charter | Expert Judgment | Cost Management Plan |  |  |  | Project Management Plan | Expert Judgment | Work Performance Information
|  |  |  | Project Management Plan | Data Analysis |  |  |  |  | Project Documents | Data Analysis | Cost Forecasts
|  |  |  | EEFs & OPAs | Meetings |  |  |  |  | Project Funding Requirements | To-Complete Performance Index | Change Requests
[10 empty] | Work Performance Data | Project Management Information System | PM Pla n Updates
|  |  |  | Estimate Costs | [5 empty] | OPAs |  | Project Documents Updates
|  |  |  | Project Management Plan | Expert Judgement | Cost Estimates
|  |  |  | Project Documents | Analogous Estimating | Basis of Estimates
|  |  |  | EEFs & OPAs | Parametric Estimating | Project Documents Updates
Bottom-Up Estimating
Three-Point Estimating
Data Analysis
Project Management Information System
Decision Making
Determine Budget
|  |  |  | Project Management Plan | Expert Judgement | Cost Performance Baseline
|  |  |  | Project Documents | Cost Aggregation | Project Funding Requirements
|  |  |  | Business Documents | Data Analysis | Project Documents Updates
|  |  |  | Agreements | Historical Information Review
|  |  |  | EEFs & OPAs | Funding Limit Reconciliation
Financing
Quality Management |  |  |  | Plan Quality Management |  |  | Manage Quality |  |  | Control Quality
|  |  |  | Project Charter | Expert Judgment | Quality Management Plan | Project Management Plan | Data Gathering | Quality Reports | Project Management Plan | Data Gathering | Quality Control Measurements
|  |  |  | Project Management Plan | Data Gathering | Quality Metrics | Project Documents | Data Analysis | Test and Evaluation Documents | Project Documents | Data Analysis | Verified Deliverables
|  |  |  | Project Documents | Data Analysis | PM Plan Updates | OPAs | Decision Making | Change Requests | Approved Change Requests | Inspection | Work Performance Information
|  |  |  | EEFs & OPAs | Decision Making | Project Documents Updates |  | Data Representation | PM Plan Updates | Deliverables | Testing/Product Evaluations | Change Requests
[5 empty] | Data Representation |  |  | Audits | Project Documents Updates | Work Performance Data | Data Representation | PM Plan Updates
[5 empty] | Test and Inspection Planning |  |  | Design for X |  | EEFs & OPAs | Meetings | Project Documents Updates
[5 empty] | Meetings |  |  | Problem Solving
Quality Improvement Methods
Resource Management |  |  |  | Plan Resource Management |  |  | Acquire Resources |  |  | Control Resources
|  |  |  | Project Charter | Expert Judgment | Resource Management Plan | Project Management Plan | Decision Making | Physical Resource Assignments | Project Management Plan | Data Analysis | Work Performance Information
|  |  |  | Project Management Plan | Data Representation | Team Charter | Project Documents | Interpersonal and Team Skills | Project Team Assignments | Project Documents | Problem Solving | Change Requests
|  |  |  | Project Documents | Organizational Theory | Project Documents Updates | EEFs & OPAs | Pre-Assignment | Resource Calendars | Work Performance Data | Interpersonal and Team Skills | PM Plan Updates
|  |  |  | EEFs & OPAs | Meetings |  |  | Virtual Teams | Change Requests | Agreements | Project Management Information System | Project Documents Updates
[9 empty] | PM Plan Updates | OPAs
Project Documents Updates
EEF Updates
OPA Updates
|  |  |  | Estimate Activity Resources |  |  | Develop Team
|  |  |  | Project Management Plan | Expert Judgment | Resource Requirements | Project Management Plan | Colocation | Team Performance Assessments
|  |  |  | Project Documents | Bottom-Up Estimating | Basis of Estimates | Project Documents | Virtual Teams | Change Requests
|  |  |  | EEFs & OPAs | Analogous Estimating | Resource Breakdown Structure | EEFs & OPAs | Communication Technology | PM Plan Updates
[5 empty] | Parametric Estimating | Project Documents Updates |  | Interpersonal and Team Skills | Project Documents Updates
[5 empty] | Data Analysis |  |  | Recognition and Rewards | EEF Updates
[5 empty] | Project Management Information System |  |  | Training | OPA Updates
[5 empty] | Meetings |  |  | Individual and Team Assessments
Meetings
Manage Team
[7 empty] | Project Management Plan | Interpersonal and Team Skills | Change Requests
[7 empty] | Project Documents | Project Management Information System | PM Plan Updates
[7 empty] | Work Performance Reports |  | Project Documents Updates
[7 empty] | Team Performance Assessments |  | EEF Updates
EEFs & OPAs
Communications Management |  |  |  | Plan Communications Management |  |  | Manage Communications |  |  | Monitor Communications
|  |  |  | Project Charter | Expert Judgment | Communications Management Plan | Project Management Plan | Communication Technology | Project Communications | Project Management Plan | Expert Judgment | Work Performance Information
|  |  |  | Project Management Plan | Communication Requirements Analysis | PM Plan Updates | Project Documents | Communication Methods | PM Plan Updates | Project Documents | Project Management Information System | Change Requests
|  |  |  | Project Documents | Communication Technology | Project Documents Updates | Work Performance Reports | Communication Skills | Project Documents Updates | Work Performance Data | Data Representation | PM Plan Updates
|  |  |  | EEFs & OPAs | Communication Models |  | EEFs & OPAs | Project Management Information System | OPAs Updates | EEFs & OPAs | Interpersonal and Team Skills | Project Documents Updates
[5 empty] | Communication Methods |  |  | Project Reporting |  |  | Meetings
[5 empty] | Interpersonal and Team Skills |  |  | Interpersonal and Team Skills
[5 empty] | Data Representation |  |  | Meetings
Meetings
Risk Management |  |  |  | Plan Risk Management |  |  | Implement Risk Responses |  |  | Monitor Risks
|  |  |  | Project Charter | Expert Judgment | Risk Management Plan | Project Management Plan | Expert Judgment | Change Requests | Project Management Plan | Data Analysis | Work Performance Information
|  |  |  | Project Management Plan | Data Analysis |  | Project Documents | Interpersonal and Team Skills | Project Documents Updates | Project Documents | Audits | Change Requests
|  |  |  | Project Documents | Meetings |  | OPAs | Project Management Information System |  | Work Performance Data | Meetings | PM Plan Updates
|  |  |  | EEFs & OPAs | [5 empty] | Work Performance Reports |  | Project Documents Updates
OPAs Updates
Identify Risks
|  |  |  | Project Management Plan | Expert Judgment | Risk Register
|  |  |  | Project Documents | Data Gathering | Risk Report
|  |  |  | Agreements | Data Analysis | Project Documents Updates
|  |  |  | Procurement Documentation | Interpersonal and Team Skills
|  |  |  | EEFs & OPAs | Prompt Lists
Meetings
Perform Qualitative Risk Analysis
|  |  |  | Project Management Plan | Expert Judgment | Project Documents Updates
|  |  |  | Project Documents | Data Gathering
|  |  |  | EEFs & OPAs | Data Analysis
Interpersonal and Team Skills
Risk Catergorization
Data Representation
Meetings
Perform Quantitative Risk Analysis
|  |  |  | Project Management Plan | Expert Judgment | Project Documents Updates
|  |  |  | Project Documents | Data Gathering
|  |  |  | EEFs & OPAs | Interpersonal and Team Skills
Representations of Uncertainty
Data Analysis
Plan Risk Responses
|  |  |  | Project Management Plan | Expert Judgment | Change Requests
|  |  |  | Project Documents | Data Gathering | PM Plan Updates
|  |  |  | EEFs & OPAs | Interpersonal and Team Skills | Project Documents Updates
Strategies for Threats
Strategies for Opportunities
Contingent Response Strategies
Strategies for Overall Project Risk
Data Analysis
Decision Making
Procurement Management |  |  |  | Plan Procurement Management |  |  | Conduct Procurements |  |  | Control Procurements
|  |  |  | Project Charter | Expert Judgment | Procurement Management Plan | Project Management Plan | Expert Judgment | Selected Sellers | Project Management Plan | Expert Judgment | Closed Procurements
|  |  |  | Business Documents | Data Gathering | Procurements Strategy | Project Documents | Advertising | Agreements | Project Documents | Claims Administration | Work Performance Information
|  |  |  | Project Management Plan | Data Analysis | Bid Documents | Procurement Documentation | Bidder Conferences | Change Requests | Agreements | Data Analysis | Procurement Documentation Updates
|  |  |  | Project Documents | Source Selection Analysis | Procurement SOW | Seller Proposals | Data Analysis | PM Plan Updates | Procurement Documentation | Inspection | Change Requests
|  |  |  | EEFs & OPAs | Meetings | Source Selection Criteria | EEFs & OPAs | Interpersonal and Team Skills | Project Documents Updates | Approved Change Requests | Audits | PM Plan Updates
[6 empty] | Make-or-Buy Decisions |  |  | OPAs Updates | Work Performance Data |  | Project Documents Updates
[6 empty] | Independent Cost Estimates |  |  |  | EEFs & OPAs |  | OPAs Updates
Change Requests
Project Documents Updates
OPAs Updates
Stakeholder Management | Identify Stakeholders |  |  | Plan Stakeholder Engagement |  |  | Manage Stakeholder Engagement |  |  | Monitor Stakeholder Engagement
| Project Charter | Expert Judgement | Stakeholder Register | Project Charter | Expert Judgment | Stakeholder Engagement Plan | Project Management Plan | Expert Judgment | Change Requests | Project Management Plan | Data Analysis | Work Performance Information
| Business Documents | Data Gathering | Change Requests | Project Management Plan | Data Gathering |  | Project Documents | Communication Skills | PM Plan Updates | Project Documents | Decision Making | Change Requests
| Project Management Plan | Data Analysis | PM Plan Updates | Project Documents | Data Analysis |  | EEFs & OPAs | Interpersonal and Team Skills | Project Documents Updates | Work Performance Data | Data Representation | PM Plan Updates
| Project Documents | Data Representation | Project Documents Updates | Agreements | Decision Making |  |  | Ground Rules |  | EEFs & OPAs | Communication Skills | Project Documents Updates
| Agreements | Meetings |  | EEFs & OPAs | Data Representation |  |  | Meetings |  |  | Interpersonal and Team Skills
| EEFs & OPAs |  |  |  | Meetings | [5 empty] | Meetings